## Sheet1
Risk ID | Risk Description | Likelihood (1-5) | Impact (1-5) | Inherent Risk | Control(s) | Residual Risk | Treatment Plan
R-001 | Unauthorized access to SaaS applications | 4 | 4 | High | MFA, RBAC, access reviews | Medium | Quarterly access certification
R-002 | Data leakage through third-party vendors | 3 | 5 | High | Vendor due diligence, DPA, NDA | Low | Annual vendor reviews, contract clauses
R-003 | System outage due to change failure | 2 | 4 | Medium | Change management policy, CAB review | Low | Expand testing, rollback plan
R-004 | Insufficient logging and monitoring of security events | 3 | 3 | Medium | Centralized SIEM, alerting rules | Medium | Tune alerts, add log sources
R-005 | Excessive admin privileges / insider threat | 3 | 4 | High | Least privilege, privilege reviews, monitoring | Medium | Quarterly privilege audits
R-006 | Unencrypted sensitive data at rest | 4 | 5 | High | Database encryption, key management | Low | Implement encryption across databases
R-007 | Unpatched operating systems and applications | 4 | 5 | High | Patch management policy, vulnerability scanning | Medium | Monthly patch cycles, critical patch SLAs
R-008 | Weak backup and recovery processes | 2 | 4 | Medium | Backup policy, DR testing | Low | Quarterly recovery drills
R-009 | Phishing and social engineering attacks | 5 | 4 | High | Email filtering, phishing simulations | Medium | Ongoing phishing tests and training
R-0010 | Inadequate employee security training | 3 | 3 | Medium | Mandatory training, awareness campaigns | Medium | Annual refresher courses, LMS tracking