## Sheet1
Control ID | Family | Requirement | Implementation Example | Evidence | Responsible Owner | Status | Planned Completion Date
3.1.1 | Access Control | Limit system access to authorized users. | RBAC enforced, MFA required. | Azure AD config, MFA logs. | IT Security | Implemented
3.1.3 | Access Control | Review and limit access rights periodically. | Quarterly access certification in Azure AD. | Access review records. | Compliance | In Progress | 2025-11-15
3.3.1 | Audit & Accountability | Create, retain, and review audit logs. | Centralized SIEM with log retention. | Sentinel logs, retention policy. | Compliance | Implemented
3.5.3 | Identification & Authentication | Enforce password complexity requirements. | GPO enforces 14+ character complexity. | GPO settings, password policy screenshots. | IT Security | In Progress | 2025-10-30
3.6.1 | Incident Response | Establish an incident response capability. | Incident Response Playbook tested quarterly. | IR reports, tabletop exercise notes. | DPO | Implemented
3.13.11 | System & Communications Protection | Employ FIPS-validated cryptography. | TLS 1.2+, AES-256 encryption enforced. | TLS config screenshots, vendor certificates. | IT Security | Implemented
3.14.1 | System & Information Integrity | Identify, report, and correct flaws. | Patch management via WSUS/SCCM. | Patch logs, vulnerability scan results. | IT Security | Implemented
3.14.3 | System & Information Integrity | Monitor system security alerts and advisories. | Subscribed to vendor alerts; patch within SLA. | Security advisories, remediation tickets. | Compliance | In Progress | 2025-12-20
3.12.1 | Security Assessment | Conduct periodic security control assessments. | Internal audits of controls performed annually. | Internal audit reports, security assessment results. | Compliance | Planned | 2026-01-15
3.11.2 | Risk Assessment | Conduct risk assessments, including threat likelihood and impact. | Risk register maintained and updated annually. | Risk assessment reports, risk register entries. | Risk Manager | In Progress | 2025-12-31