## Sheet1
Risk ID | Risk Description | Likelihood (1-5) | Impact (1-5) | Inherent Risk | Control(s) | Residual Risk | Treatment Plan
GDPR-001 | Non-compliance with lawful, fair, and transparent processing (Art. 5) | 3 | 5 | High | Privacy Policy, Consent Management System | Medium | Quarterly privacy audits, consent log reviews
GDPR-002 | Incomplete records of processing activities (Art. 30) | 2 | 4 | Medium | Records of Processing Register (RoPA) | Low | Annual RoPA updates and compliance review
GDPR-003 | Weak security of processing measures (Art. 32) | 4 | 5 | High | Encryption, Access Controls, DRP | Medium | Quarterly DR tests, regular encryption audits
GDPR-004 | Delayed or missed breach notification to authority (Art. 33) | 3 | 5 | High | Incident Response Plan, Breach Notification SOP | Medium | Tabletop breach simulation, 72h notification tests
GDPR-005 | Failure to honor data subject rights (Art. 15-22) | 3 | 4 | Medium | DSAR process, DPO oversight | Medium | Employee training, quarterly DSAR checks
GDPR-006 | Inadequate consent management (Art. 7) | 4 | 4 | High | Consent forms, preference center | Medium | Annual consent review, transparency reports
GDPR-007 | Unencrypted transmission of personal data (Art. 32) | 3 | 5 | High | TLS, VPN, encryption standards | Medium | Annual encryption audit, TLS upgrades
GDPR-008 | Lack of Data Protection Impact Assessments for high-risk processing (Art. 35) | 2 | 4 | Medium | DPIA procedures, risk assessments | Low | DPIA for all high-risk projects
GDPR-009 | Excessive data retention beyond necessity (Art. 5) | 3 | 3 | Medium | Retention schedules, deletion policy | Low | Quarterly deletion reviews
GDPR-0010 | Third-party vendor non-compliance with GDPR (Art. 28) | 4 | 5 | High | Vendor contracts, Data Processing Agreements (DPAs) | Medium | Vendor due diligence, yearly GDPR compliance certification